## Sheet1
StreetFoodLove Software Testing Document
Test Case ID | Requirement | Precondition | Steps | Test Data | Expected Result | Actual Result | Pass/Fail | Tester | Date
1 | Map markers | None | 1. Go to the map page at / (index) 2. Move the map so that all of Bellevue is visible | Data for street food vendors that are in Bellevue | All map markers and/or popups for vendors in Bellevue are visible in the correct locations | As expected | Pass | Makoto Emura | 2021-11-30
2 | Map marker selection | The map is opened and a marker is visible | 1. Hover over a map marker 2. Click on the marker | Data for street food vendors | When the cursor hovers over a marker, the name of the vendor for that marker appears near the marker. When the marker is clicked, the vendor popup appears. | When the cursor hovers over a marker, the vendor name does not appear. | Pass | Makoto Emura | 2021-11-30
3 | Map popup selection | The map is opened and a popup is visible | 1. Click anywhere inside a map popup | Data for street food vendors | The vendor page is opened | Nothing happens | Pass | Makoto Emura | 2021-11-30
4 | Login | Login page is opened | 1. Add a test user into the User table 2. In the username field, add the test user's username 3. In the password field, add the test user's password 4. Click on the Login button | Test user | The app redirects to the previous page in the browsing history, and a status popup says that the user has logged in. | No indication to show that the user has logged in | Pass | Makoto Emura | 2021-11-30
5 | Login with invalid credentials | Login page is opened | 1. Enter the letter "a" into the username and password fields 2. Click on the Login button | None | The login interface remains visible and an easy-to-understand error message appears below the Login button which says that the username and/or password is incorrect. | An error does appear, though the message should be improved to be more user-friendly | Pass | Makoto Emura | 2021-11-30
6 | Offline | The development build is used and login page is opened | 1. Stop the backend process 2. Click the Login button in the login UI | None | After a possible delay, a status popup appears which says that the user may be offline | An error does appear but it is hard to understand | Pass | Makoto Emura | 2021-11-30
7 | Create User table, Vendor table, Reviews table in the database | User table, Vendor table, Review table will be created in the database | 1. Call the "SetupTables()" function to create the User, Vendor, and Reviews table | See Sheet2 | After calling those functions, the correct tables are created in the database | 3 tables are created (See the pictures in the back) | Pass | Wenhuan Tan | 2021-11-26
8 | Insert testing data to the User, Vendor, Reviews tables | Testing data can be inserted to the User, Vendor, Reviews tables | 1. Call the backend functions "UserCreate()", "VendorCreate()", and "ReviewCreate()" to insert the data given in the test data | See Sheet2 | After call these functions, the testing data are inserted to the tables | Data are inserted to tables (See the pictures in the back) | Pass | Wenhuan Tan | 2021-11-26
9 | Review the data inserted to the tables in the Database | Testing data can be reviewed by MySql select statement | 1. Add the test data to the database 2. Call the backend functions "User()", "Vendor()", and "User()" to retrieve all of the test data by primary key | See Sheet2 | All of the correct records are retrieved | We can review the testing data in MySql | Pass | Wenhuan Tan | 2021-11-26
10 | Reviews submitted in frontend | Reviews can be submitted successfully after clicking Submit Review button | 1. Login in. 2. Click on the Write Review button. 3. Fill out review sections 4. Click Submit Review button. | User entered data, | Review is successfully submitted, the form template is closed, and the newly written review is displayed in a stacked list near the bottom of the page. | Can create a new review using the create review button | Pass | Colin Zhou | 2021-11-30
11 | Review the data inserted to the tables in the Database | After customer submit reviews, the reviews will be instored into our database | 1. Login in. 2. Click on the Write Review button. 3. Fill out review sections 4. Click Submit Review button. 5. Refresh SQL | Data that user entered in review template | Review will populate in SQL under the Review Table | Submitted review populated in SQL under the Review Table | Pass | Silvia Casaburi | 2021-11-30
12 | Sign-up | None | 1. Go to sign-up page 2. Fill in all fields with valid test user details and click on submit button 3. Log out and log in with the credentials that were submitted on the sign-up page | Test user | After the submit button is clicked, the app should open a page which says that the user was created and that the account needs to be verified by email. The log in step should succeed using the credentials provided during sign-up. | As expected | Pass | Makoto Emura | 2021-11-30
13 | Search bar | OpenSearch engine is implemented successfully | 1. Enter vendor name to be searched in the field | user entered data | The vendor will appear on the left side of the map | As expected | Pass | Wenhuan Tan | 2022-02-27
14 | Search result filtering and sorting | OpenSearch engine is implemented successfully | 1. Check one or some filtering and sorting conditions 2. Click search button | Vendor table in the database | The search results are presented as filtering and sorting condition | As expected | Pass | Wenhuan Tan | 2022-03-01
15 | Search history | None | 1. Click in search box and type in a string | Vendor table in the database | If the string matches a substring of a recent search, the resent search appears in the search box | As expected | Pass | Wenhuan Tan | 2021-11-30
16 | Geolocation tracking | Geolocation tracking and map is implemented | 1. Open the vendor page 2. Check whether the current location is shown on the map 3. Check whether the time of the latest location update is shown such as "Updated 3 minutes ago" | Vendor table in the database | The location and time of the latest update is shown on the map | Location input in customize vendor page | Pass | Wenhuan Tan | 2021-11-30
17 | Email verification for sign-up | Simple Email Service | 1. User/Vendor will sign up for app 2. Verification code will be send to the customers phone number or email address | Login information | Customer receives verification either as a text message on the phone or email | Will not implement | Fail | Silvia Casaburi | 2021-11-30
18 | Favorites list | None | 1. Click on the heartshape to like a vendor 2. Vendor will be added to the Favorite List | Test vendor information | In the user account, under the favorite list the vendor liked will be listed | As expected | Pass | Silvia Casaburi | 2022-03-01
19 | Photo library on vendor page | AWS S3 | 1. Click a vendor page 2. Check whether you can see the photos about their food, menus, and how it look like from outside | Vendor table in the database | The customers can see photos of the street food vendors | As expected | Pass | Wenhuan Tan | 2022-03-01
20 | "Like" pictures | None | 1. Click the heart-shaped button on the picture once 2. Click the hearted-shaped button one more time | Vendor table in the database | The heart-shaped button on the pictures turn red if you click one time and it will turn gray if you click one more time | Will not implement | Fail | Wenhuan Tan | 2021-11-30
21 | Notifications | None | 1. Prepare notifications for some specific vendors 2. Send the notifications to vendors 3. Check vendor account to see whether notifications are shown in the vendor account page | Vendor table in the database | The notification can be shown in vendors' account page after we sent | Vendors can get notifications about new reviews | Pass | Wenhuan Tan | 2021-11-30
22 | Food recommendation | Favorite list like function | 1. User likes a food or vendor | Test user and test vendor | app will recommend food previously liked | In search results | Pass | Silvia Casaburi | 2021-11-30
23 | Settings | A test user is created and logged in | 1. Go to account settings page 2. Leave all fields as is except the first name, which should be changed to a non-empty string 3. Click on the Change Settings buttons | Test user | In the profile information, the first name is changed to the new string | As expected | Pass | Makoto Emura | 2021-03-01
24 | Single sign-on | OAuth2 client is implemented | 1. In the sign-up page, click on the Continue with Google button 2. In the Google authorization page, click the Accept button 3. After the app redirects to the sign-up page, enter valid user information in the user info fields and click Create Account 4. Log out and log in with Google account | Google account | After accepting the Google account authorization, the sign-up page on our app should open. After sign-up, the Google account can be used to log in. | Sign-in with Google works; there is no need to fill out a create account page. | Pass | Makoto Emura | 2022-02-15
25 | Analytics | Vendor exists and some sample data is added to the database | 1. Login as a vendor | Test vendor | Dashboard will display different data points, such as average rating increase or decrease, search queries, clicks | Charts are shown | Pass | Silvia Casaburi | 2021-11-30
26 | Vendor dashboard | Vendor sign up functionality has been implemented | 1. Login as a vendor | Test vendor login information | The dashboard displays links to own vendor page and edit vendor page | As expected | Pass | Silvia Casaburi | 2021-11-30
27 | Business guides | The business guide documents or tutorial videos are ready | 1. Collect business guides from online 2. write instruction documents 3. create tutorial videos if needed 4. Add the the documents and videos into our web app | None | The business guides can be found in the buttom of our website | We have 6 guides | Pass | Wenhuan Tan | 2021-11-30
28 | Live chat | Vendor must exist | 1. Login 2. Go to Vendor's Page 3.Click on live chat on the bottom right corner | none | Communication between vendor and user | Will not implement | Fail | Silvia Casaburi | 2021-11-30
29 | Share on social media | 1. Mobile app is implemented 2. our mobile app is able to link to social media 3. The user have logined into social media application in their mobile phone | 1. Search for a vendor 2. View the vendor page 3. Click the share button on the top right corner of the vendor 4. choose the right social media from the drop-down menu | None | The vendor page information can be shown on social media after I click share button on the top right corner of the vendor page | Vendor pages can be shared | Pass | Wenhuan Tan | 2021-11-30
30 | Push notification | Mobile app is implemented, Amazon SNS is configured | 1. Enable push notifications on mobile app 2. Enable notifications for new food trucks nearby 3. Add a test vendor near the testing location | Test vendor | Push notification appears on phone within 2 minutes of activation, which says that the vendor just arrived nearby | Will not implement | Fail | Makoto Emura | 2021-11-30
31 | Invite friends | Mobile App implementation | 1. Login 2. Send friends invite to email or phone number | Test User | Friend receives an email or text message notification | Will not implement | Fail | Silvia Casaburi | 2021-11-30
32 | Discounts/vouchers | 1. Vendor must exist 2.Discount system must be implemented 3. Vendor enables option to give discounts in exchange of reviews | 1. Login 2. Go to Vendor page 3. Submit Review | Test user | After submitting a review a voucher/discount will be received | As expected | Pass | Silvia Casaburi | 2021-11-30
33 | QR codes for vouchers | Discount/Voucher functionality has been implemented | 1. Login 2. Go to Vendor's Page 3.Submit Review | Test user and test vendor | QR code has been added to the QR list | As expected | Pass | Silvia Casaburi | 2021-11-30

## Sheet2
Vendor Table
ID | Name | BusinessAddress | Website | BusinessHours | Phone | BusinessLogo | Latitude | Longitude
"e72ac985-3d7e-47eb-9f0c-f8e52621a708" | "vendor0" | "address0" | "www.vendor0.com" | "Mon-Sun 8:00AM-5:00PM" | "123-123-1234" | "image0_url" | "47.608013" | "-122.335167"
"b924349d-442f-4fff-984e-ab0ec36f4590" | "vendor1" | "address1" | "www.vendor1.com" | "Mon-Sun 8:00AM-5:00PM" | "321-321-4321" | "image1_url" | "47.982567" | "-122.193375"
User Table
ID | Email | Username | FirstName | LastName | SignUpDate | LoginPassword | UserType | Photo
"02c353e2-e0f5-4730-89c7-b0a0610232e4" | "seventan2516@gmail.com" | "Selina2516" | "Selina" | "Tan" | "2021-11-23 11:45" | "JINSIWDW234" | 0 | "image-1url"
"c8936fa6-69b7-4bf8-a033-a1056c80682a" | "jonney2313@hotmail.com" | "Jonney2313" | "Jonney" | "William" | "2021-11-25 16:25" | "738djsuw*dwd" | 0 | "image-5url"
Reviews Table
ID | Text | VendorID | UserID | DatePosted
"414569e0-8785-4131-8e13-43a9b7d8208d" | "The soup is super creamy and tasty and the chicken wings are so delicious" | "b924349d-442f-4fff-984e-ab0ec36f4590" | "c8936fa6-69b7-4bf8-a033-a1056c80682a" | "2021-11-26 09:34:00"
"398b174f-9e2f-4f7d-a179-bb86986227b5" | "The dumplings and ramen are supper delicious" | "e72ac985-3d7e-47eb-9f0c-f8e52621a708" | "02c353e2-e0f5-4730-89c7-b0a0610232e4" | "2021-11-26 10:26:00"